Weekly Report #2

Date: 9/19/2011

Project Name: Virtual Finger

Group Number: 36

Group Members: Ashley Williams, Catie Reynolds, Jill Greenfield

Current status of project:

- Have list of design ideas with a few that we are focusing on

- Have website up and running

- Decided that it is best to hold off on human testing until necessary

Work completed in the last week:

- Came up with list of 8 solid project ideas

- Met with our mentor, Dr. Hullar, in person to discuss scope of project and get feedback on design ideas

Work planned for next week:

- Look into ways to prevent public disclosure throughout coursework

- Read literature on ankle braces/motion sensors for one project idea

- Make website private

- Begin working on first paper

Anything needed from mentor/client or TA or instructor to continue work: need to discuss IP - ways we can prevent public disclosure while still completing coursework required; will set up meeting with Dr. Klaesner and Dr. Anastasio to discuss this as soon as possible